**ANCIEN: tasks and deadlines, December 2011**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Deadlines** | **Received** | **Scientific Coordinators Review** | **Edited** | **Published** |
| **WP2** | | | | | |
| **Combined report for 2.2&2.3** | **9 December 2011** | 21 Nov 2011 | FPB |  |  |
| **Policy Brief** | **9 December 2011** |  |  |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables (if any)** | **15 December 2011** |  |  |  |  |
| **WP3** | | | | | |
| **Final Report: Summary report by FEDEA** | **9 December 2011** | 31 Jul 2011 | FPB |  |  |
| **Policy brief** | **9 December 2011** | 31 Jul 2011 | FPB/CPB |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables (if any)** | **16 December 2011** | 25 Nov 2011 | Pending…  Est. feedback:  9 December 2011 |  |  |
| **WP4** | | | | | |
| **Del. 4.1 Technological solutions potentially involved in LTC activities** | **16 December 2011** | 21 Nov 2011 | Pending…  Est. feedback:  9 December 2011 |  |  |
| **Del. 4.2 Role and potential impact of technology** | **16 December 2011** | 28 Nov 2011 | Pending…  Est. feedback:  9 December 2011 |  |  |
| **Policy Brief** | **9 December 2011** |  |  |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables** | **16 December 2011** |  |  |  |  |
| **WP5** | | | | | |
| **Deliverable 5.1** | **16 December 2011** | 14 Nov 2011 | Est. feedback:  7 December 2011 |  |  |
| **Deliverable 5.2** | **16 December 2011** | 14 Nov 2011 | Est. feedback:  7 December 2011 |  |  |
| **Policy Brief** | **9 December 2011** |  |  |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables (if any)** | **16 December 2011** |  |  |  |  |
| **WP6** | | | | | |
| **LSE** | June 11  before 5th Workshop | Draft report on projection of informal LTC supply: June 11 |  |  |  |
| **CPB, DIW, FEDEA, CASE** | Spring 11  end Aug11 | Institutionalisation models | **n.a.** | **n.a.** | **n.a.** |
| **LEGOS -report on institutionalization based on DIW, FEDEA, CPB and CASE estimates.** | Spring 11  end of Sep11  **Final: 9 December 2011** | A draft note on institutionalisation by LEGOS,  Nov 2011 | FPB/CPB |  |  |
| **CPB, DIW, FEDEA, CASE** | Spring 11  end Aug11 | Formal care labour supply estimations: **CASE and FEDEA projection data before**  **6 December 2011** | **n.a.** | **n.a.** | **n.a.** |
| **LEGOS report on the formal care labour supply projections based on DIW, FEDEA, CPB and CASE estimates.** | Spring 11  end of Oct11  **Final text incl. SP and PL: 16 Dec 2011** | Note 10 Nov 2011 | FPB/CPB |  |  |
| **Projections report (FPB)** | Oct 2011  **Draft final report: 16 december 2011** |  |  |  |  |
| **Policy scenarios report (FPB)** | Spring 2012 |  |  |  |  |
| **Policy brief (FPB)** | **23 Dec 2011** |  |  |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables (if any)** | **16 December 2011** |  |  |  |  |
| **WP7** | | | | | |
| **Working paper on individual outcome results (CPB)** | **Mid March 2012** |  |  |  |  |
| **Integration previous WPs (Tarki)** | **February 2012** |  |  |  |  |
| **Data collection (Tarki)** | **February 2012** |  |  |  |  |
| **Analysis equity and financing (LSE)** | **February 2012** |  |  |  |  |
| **Working paper on results of system levels (LSE)** | **Mid March 2012** |  |  |  |  |
| **Country feedback** | **Mid April 2012** |  |  |  |  |
| **Final report** | **July 2012** |  |  |  |  |
| **Policy brief (CPB)** | **August 2012** |  |  |  |  |
| **Publishable summary for the 2nd Periodic Report; explanations for delays and changes in deliverables (if any)** | **15 December 2011** |  |  |  |  |

**Some dates that were agreed on:**

* Steering Committee meeting: January 2012
* WP7 Workshop in the Hague: **24 February 2012 or (2 March 2012**)
* 6th Workshop: **26-27 April 2012 (**or **3-4 May 2012**) in Istanbul or in the Hague
* Final Conference: **3rd/4th week of October 2012**, CEPS
* Two Clustered Seminars:

**- 2 October 2011 (or 9 October 2012** in Paris; **4 October 2012 (or 11 October 2012**) in Rome and (Roberto and Jérôme will check the availability of the Conference room)

- Alternatively in Vienna or in Bratislava (Markus and Marek will check the availability of the Conference room)